2017 Performance Improvement Report

STRATEGIC PRIORITY

3. Improve efficiency and decision-making

|  |  |  |  |
| --- | --- | --- | --- |
| **Project Name** | | | |
| **Reduce Catheter Associated Urinary Tract Infection (CAUTI) in A2** | | | |
| **Site** | | **Department** | |
| Riyadh | | Nursing Pediatric- A2 | |
|  | | | |
| **Project Status** | **Project Start Date** | | **Project End Date** |
| Completed | 10-01-2016 | | 09-30-2017 |

|  |  |
| --- | --- |
| **Problem:** Why the project was needed?  Reduce the risk of healthcare associated infections is the International Patient Safety Goal #5. A2 staff worked on reinforcing the hospital specific standards of nursing care on urinary catheter insertion, maintenance and removal care especially after the increase of CAUTI up to 10.9 in A2 unit. | **Aims:** What will the project achieve?  Reduce CAUTI Infection rate from 10.9 to 0 in A2 before the end of 3Q 2017 |
| **Benefits/Impact:** What is the improvement outcome?  *(check all that apply)*  Contained or reduced costs  Improved productivity  Improved work process  Improved cycle time  Increased customer satisfaction  Other (please explain)  Click or tap here to enter text. | **Quality Domain:** Which of the domains of healthcare quality does this project support?  *(Select only one)*  **Efficient** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| |  |  | | --- | --- | | **Measures:** Performance metrics to be evaluated | **Targets:** Expected outcomes | | **CAUTI Infection Rate** | **Zero** | |
| **Interventions:** Overview of key steps/work completed   * Formulation of A2 CAUTI task force * In‐services on Urinary Catheter maintenance provided when needed. * Development of urinary catheter maintenance competency check off. * Education material developed and uploaded to unit   shared file.   * Random unit audit performed. * Daily review of urinary catheter is checked. |
| **Results:** Insert relevant graphs and charts to illustrate improvement pre and post project  *(insert relevant graphs, data, charts, etc.)* |

|  |  |
| --- | --- |
| **Project Lead** | **Team Members** |
| **Name**  *(person accountable for project)* | **Names**  *(persons involved in project)* |
| Yasser Qadous, AAHN | Jasmin, Erlinda-SN 1  Ismail, Hodan-SN1  Hinola, Jo-SN1  Canoy,Virna marie-SN 1  De francia, Jelly marie-SN1  Villanueva,Analyn-SN1  Mirabueno,Emily-SN1 |