2017 Performance Improvement Report

STRATEGIC PRIORITY

 1. Develop world-leading healthcare and research

|  |
| --- |
| **Project Name** |
| Reduce Fall Incident in Pediatrics Oncology |
| **Site** | **Department** |
| Jeddah | Pediatric Oncology |
|  |
| **Project Status** | **Project Start Date** | **Project End Date**  |
| Completed | 03-23-2016 | 12-31-2016 |

|  |  |
| --- | --- |
| **Problem:** Why the project was needed?Poor staff compliance to falls assessment/reassessment. | **Aims:** What will the project achieve?reduce the incidence by 10% per each quarter |
| **Benefits/Impact:** What is the improvement outcome?*(check all that apply)*[ ]  Contained or reduced costs[ ]  Improved productivity[ ]  Improved work process[ ]  Improved cycle time[ ]  Increased customer satisfaction[x]  Other (please explain) Improve patient safety | **Quality Domain:** Which of the domains of healthcare quality does this project support?*(Select only one)***Safe** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
| **Measures:** Performance metrics to be evaluated | **Targets:** Expected outcomes |
| Fall Risk Assessment | Reduce the incidence by 10% per each quarter |

 |
| **Interventions:** Overview of key steps/work completed* A questionnaire has been developed utilizing evidence-based practice of pediatric nurses partnering with parents to reduce falls incident in inpatient pediatric oncology unit.
* Three articles has been reviewed from ProQuest Nursing & Allied Health Database, and another article reviewed from The Joanna Briggs Institute to identify the best evidence for fall risk prevention.
* Multi-language fall prevention poster placed in all patient room.
* Partnership safety agreement with patient parents/sitter of fall prevention to be sign by parents/caregiver and primary nurse upon admission.
* To provide a copy of fall prevention education tool in Arabic version to parents/caregiver.
 |
| **Results:** Insert relevant graphs and charts to illustrate improvement pre and post project*(insert relevant graphs, data, charts, etc.)*  |

|  |
| --- |
| **PONC (Pediatric Oncology)** |
| **Monthly Nursing Performance Measures** |
| **Measures** | **Internal Trigger** | **Jan-16** | **Feb-16** | **Mar-16** | **Apr-16** | **May-16** | **Jun-16** | **Jul-16** | **Aug-16** | **Sep-16** | **Oct-16** | **Nov-16** | **Dec-16** |
| **Total FALLS** | 1.1/1000 patient days | 3.5 | 1.8 | 3.4 | 0.0 | 0.0 | 0.0 | **1.7** | **1.9** | **0.0** | **1.7** | **0.0** | **0.0** |
| **Falls with injury** | 1.1/1000 patient days | 3.5 | 1.8 | 0.0 | 0.0 | 0.0 | 0.0 | **1.7** | **0.0** | **0.0** | **0.0** | **0.0** | **0.0** |



|  |  |
| --- | --- |
| **Project Lead** | **Team Members** |
| **Name** *(person accountable for project)* | **Names***(persons involved in project)* |
| Shara ALHarbi  | Bigy RaphaelLinda OthamnKristy NediraEmma Araya Shoinse Young Abeer AljoudyGillian Sedgewick, Amal Al-Othmani Ohood Al-Haddad  |