2017 Performance Improvement Report

STRATEGIC PRIORITY

1. Develop world-leading healthcare and research

|  |  |  |  |
| --- | --- | --- | --- |
| **Project Name** | | | |
| Improving of the of Lead Apron & Garments Tracking | | | |
| **Site** | | **Department** | |
| Jeddah | | Radiology Department /Angiography | |
|  | | | |
| **Project Status** | **Project Start Date** | | **Project End Date** |
| Completed | 04-01-2017 | | 08-22-2017 |

|  |  |
| --- | --- |
| **Problem:** Why the project was needed?  No systematic method to confirm the inspection, cleaning and the safety of the lead aprons& garments usage among (Dental, Radiology ,OR and Cath. Lab ), only Radiology department was tracking their lead aprons which is122 pieces, we will target a total of 423 pieces including (Dental, Radiology, OR and Cath. Lab ). | **Aims:** What will the project achieve?  Improving the compliance of lead apron & garments tracking. |
| **Benefits/Impact:** What is the improvement outcome?  *(check all that apply)*  Contained or reduced costs  Improved productivity  Improved work process  Improved cycle time  Increased customer satisfaction  Other (please explain)  Click or tap here to enter text. | **Quality Domain:** Which of the domains of healthcare quality does this project support?  *(Select only one)*  **Safe** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| |  |  | | --- | --- | | **Measures:** Performance metrics to be evaluated | **Targets:** Expected outcomes | | Compliance of lead apron & garments tracking | Improving the compliance of lead apron & garments tracking from 28% to 100% by the end of August 2017 | |
| **Interventions:** Overview of key steps/work completed   * A software for lead apron tracking was designed and installed in each department (Dental, Radiology, OR and Cath. Lab). * A team leader was assigned for each department (Dental, Radiology, OR and Cath. Lab) * The assigned staffs were trained on how to utilize the software. A follow up on progress was done. * Lead aprons were labeled, tagged and linked to the tracking system (Radiation Protection Garments Quality Control software). * All lead aprons were tagged. |
| **Results:** Insert relevant graphs and charts to illustrate improvement pre and post project  *(insert relevant graphs, data, charts, etc.)* |

|  |  |
| --- | --- |
| **Project Lead** | **Team Members** |
| **Name**  *(person accountable for project)* | **Names**  *(persons involved in project)* |
| Ehab Ababneh | Mahmoud Ali  CINI ALIAS  SAMUEL JR GO  EVELYN SINAJON  Iman Mohammed  Ibrahim Qoulaghasi |