2017 Performance Improvement Report

STRATEGIC PRIORITY

2. Increase capacity and patient access

|  |  |  |  |
| --- | --- | --- | --- |
| **Project Name** | | | |
| Enhancing Admissions for Patient on Waiting List. | | | |
| **Site** | | **Department** | |
| Riyadh | | Registration Appointment & Admission Services in collaboration with Medical & Clinical Affairs (MCA) and Case Management | |
|  | | | |
| **Project Status** | **Project Start Date** | | **Project End Date** |
| Completed | 01-01-2017 | | 09-30-2017 |

|  |  |
| --- | --- |
| **Problem:** Why the project was needed?  The previous admission waiting list categories were limited to two options:   * Elective where patient had to be seen within a maximum of 90 days), and * Urgent where patient to be seen within a maximum of 30 days).   This limitation was a challenge for physicians because there was no link between patient conditions and the available categories; consequently, patient safety could be compromised due to long admission waiting time with no proper follow up. | **Aims:** What will the project achieve?  Decrease the percentage of exceeded case for admission (90 for elective or 30 for urgent) by at least 5% from the baseline before the end of 2017. |
| **Benefits/Impact:** What is the improvement outcome?  *(check all that apply)*  Contained or reduced costs  Improved productivity  Improved work process  Improved cycle time  Increased customer satisfaction  Other (please explain)  Click or tap here to enter text. | **Quality Domain:** Which of the domains of healthcare quality does this project support?  *(Select only one)*  Patient Centred |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| |  |  | | --- | --- | | **Measures:** Performance metrics to be evaluated | **Targets:** Expected outcomes | | Admission Exceeded Cases | At least < 5% from baseline | |
| **Interventions:** Overview of key steps/work completed   * Development of new categories for the admission waiting list based on patient’s condition (A to F) where class A is for the shortest waiting time (within 48 hrs) and class F is for a waiting time that should not exceed 365 days. * Re-evaluation of all patients classified on the old category admission waiting list and re-classify them on the new list based on their conditions. * Weekly checking of the admission waiting list by Case Managers to ensure proper compliance to the new admission waiting list categories. * All relevant departments’ chairmen, in both Jeddah and Riyadh, have been informed of the new changes to the admission waiting list and have been provided with the needed information in respect to their roles. |
| **Results:** Insert relevant graphs and charts to illustrate improvement pre and post project  *(insert relevant graphs, data, charts, etc.)*   |  |  |  |  | | --- | --- | --- | --- | | CATEGORY | TOTAL NUMBER OF CASES | EXCEEDED CASES | PERCENTAGE | | OLD CATEGORIES (Before September2017) | | |  | | ELECTIVE | 406 | 265 | 65% | | URGENT | 74 | 56 | 75% | | NEW CATEGORIES (After September2017) | | |  | | CLASS A | 2 | 2 | 100% | | CLASS B | 16 | 10 | 62% | | CLASS C | 75 | 52 | 69% | | A,B,C equivalent to previous URGENT CATEGORY | 93 | 64 | 68% | | CLASS D | 38 | 19 | 50% | | CLASS E | 42 | 1 | 0.20% | | CLASS F | 277 | 119 | 43% | | D,E,F = equivalent to previous ELECTIVE CATEGORY | 357 | 139 | 39% | |
|  |

|  |  |
| --- | --- |
| **Project Lead** | **Team Members** |
| **Name**  *(person accountable for project)* | **Names**  *(persons involved in project)* |
| Dr. Mohamed Al Otaibi | Dr. Tahani AlShayea  Hanan AlSaif  Saleh AlBothi  Khalid AlSaif  Mansour AlSahali  Seba AbuLesan  Falah AlHarbi  Anwar AlQahtani  Nayef AlSubaie,  Mohammed AlQahtani,  Saud AlAjmi,  Bandar Rashwan (Jeddah) |